## Test summary report
Tester | Ngô Quốc Quý, Nguyễn Trần An Hòa, Nguyễn Thuận Phát, Tô Khánh Linh, Phạm Phú Toàn
Date | 25/08/2023
function tested | total test case | test case passed | test case failed | bug | open | close
7 | 26 | 23 | 3 | 3 | 0 | 3
in details
reading comic | 4 | 4 | 0 | 0 | 0 | 0
create comic | 4 | 3 | 1 | 0 | 0 | 1
upload chapter | 5 | 4 | 1 | 0 | 0 | 1
create group | 3 | 2 | 1 | 1 | 0 | 1
comment | 4 | 4 | 0 | 0 | 0 | 0
Searching comic | 3 | 3 | 0 | 0 | 0 | 0
rating | 3 | 3 | 0 | 0 | 0 | 0

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | Error message not shown | When uploader does not choose chapter image and clicks "Lưu", system catch an error instead of showing error message | UC03 | high | Nguyễn Thuận Phát | 25/08/2023 | Closed
B002 | Wrong error message | Website show the message which require user to fill in the group name field instead of the message requires users not leaving the fields empty | UC04 | low | Nguyễn Trần An Hòa | 25/08/2023 | Closed
B003 | Wrong error message | The error message does not tell exactly which field is missing information | UC02 | low | Tô Khánh Linh | 25/08/2023 | Closed